## Template
Matrix for Site Administration and Communication
Guideline for Site Administration and Communication
No. | Description of Activities | Contractor | Consultant | Owner
1 | Communication
| 1.1 General Correspondence | P | P | P
| 1.2 Site Instruction | D | P | C
| 1.3 Site work instruction | D | P/B | A
| 1.4 Request for information | P | A | C
| 1.5 Request for modification | P | B | A
2 | Submittals
| 2.1 Subcontractor | P | B/R | A
| 2.2 Materials | P | A | C
| 2.3 Shop Drawings | P | A | C
| 2.4 Staff Approval | P | B | A
| 2.5 Premeeting submittals | P | D | C
3 | Plans and Programs
| 3.1 Construction schedule | P | R | C
| 3.2 Submittal logs | P | R | C
| 3.3 Procurement logs | P | R | C
| 3.4 Schedule update | P | R | C
4 | Monitor and Control
| 4.1 Progress | D | P | C
| 4.2 Time | D | P | C
| 4.3 Payments | P | R/B | A
| 4.4 Variations | P | R/B | A
| 4.5 Claims | P | R/B | A
5 | Quality
| 5.1 Quality control plan | P | R | C
| 5.2 Checklists | P | D | C
| 5.3 Method statements | P | A | C
| 5.4 Mock-up | P | A | B
| 5.5 Samples | P | A | B
| 5.6 Remedial notes | D | P | C
| 5.7 Nonconformance report | D | P | C
| 5.8 Inspections | P | D | C
| 5.9 Testing | P | A | B
6 | Site Safety
| 6.1 Safety program | P | A | C
| 6.2 Accident report | P | R | C
7 | Meetings
| 7.1 Progress | E | P | E
| 7.2 Coordination | E | P | C
| 7.3 Technical | E | P | C
| 7.4 Quality | P | C | C
| 7.5 Safety | P | C | C
| 7.6 Closeout |  | P
8 | Reports
| 8.1 Daily report | P | R | C
| 8.2 Monthly report | P | R | C
| 8.3 Progress report |  | P | A
| 8.4 Progress photographs |  | P | A
9 | Closeout
| 9.1 Snag list | P | P | C
| 9.2 Authorities' approval | P | C | C
| 9.3 As-built drawings | P | D/A | C
| 9.4 Spare parts | P | A | C
| 9.5 Manuals and documents | P | R/B | A
| 9.6 Warranties | P | R/B | A
| 9.7 Training | P | C | A
| 9.8 Handover | P | B | A
| 9.9 Completion certificate | P | B/P | A
Legend: | A, approve; B, advise/assist; C, information; D, action; E, attend; P, prepare/initiate; R, review/comment