## Sheet1
Management of Risks during Construction Phase
No. | Description of Risk | Mitigation of Risk
1. | Low-bid project cost | Competitor to try competitive material, improve method statement and higher production rate from manpower
2. | Incompetent subcontractor | The Contractor has to monitor the workmanship and work progress
3. | Failure of team members not performing as expected | Select competent candidates and provide training.
4. | Delay in site handover | Contractor to adjust the construction schedule
5. | Delay in site mobilisation | The construction schedule should be adjusted accordingly
6. | Scope/design changes | Resolve change order issues in order not to delay the project
7. | Different site conditions to the information provided | Contractor to investigate site conditions prior to starting the relevant activity
8. | Inadequate site investigation data | Contractor to investigate site conditions prior to starting the relevant activity
9. | Conflict in contract documents | Resolve the issue amicably (contractor and client)
10. | Incomplete design | Raise a request for information (RFI) to client
11. | Incomplete scope of work | Raise an RFI to client
12. | Incomplete specifications | Raise an RFI to client
13. | Design changes | Follow the contract documents for a change order
14. | Errors and omissions in contract documents | Raise an RFI to Client
15. | Inappropriate construction method | Raise an RFI and correct the method statement
16. | Delay in change order negotiations | Request the client/project manager to expedite negotiations and resolve issues
17. | Change in laws and regulations | Contractor to inform the client and raise an RFI
18. | Statutory or regulatory delay | Regular follow-up by the contractor or client with the regulatory institution
19. | Project schedule | Compress the duration of activities (accelerate works)
20. | Inappropriate schedule | Contractor to prepare a schedule taking into account all site conditions and required parameters
Creater by : GLOQ CONSTRUCTION & PROJECTS